## Plan1
Tarefa | Horas Planejadas | Horas Gastas |  | Sprints | Planed Value (PV) | Actual Cost (AC) | Earned Value (EV) | Dia | Sprints | Tarefas | Horas | Horas Gastas
Levantamento de Requisitos | 15 | 15 |  | 0 | 0 | 0 | 0 | 2016-09-19 | 1 | Levantamento de Requisitos | 15 | 15
Elaboração de modelos | 25 | 25 |  | 1 | 40 | 40 | 40 |  |  | Elaboração de modelos | 25 | 25
Definir cronogramas | 2 | 3 |  | 2 | 64 | 63.7 | 64 | 2016-10-03 | 2 | Especificar custos | 15 | 12.5
Análise de riscos | 1 | 1.5 |  | 3 | 89 | 70.2 | 76 |  |  | Definir cronogramas | 2 | 3
Especificar custos | 15 | 12.5 |  | 4 | 108 | 77.2 | 90 |  |  | Definir orçamento | 2 | 1.5
Definir orçamento | 2 | 1.5 |  | 5 | 130 | 91.2 | 121 |  |  | Análise de riscos | 1 | 1.5
Verifica jogada | 12 | 6.5 |  | 6 | 167 | 140.7 | 153 |  |  | Slides 1 | 2 | 3.5
Verifica status | 5 | 3 | - | 7 | 205 | 232.2 | 205 |  |  | Apresentacao 1 | 2 | 1.7
Controller | 5 | 7 | - |  |  |  |  | 2016-10-17 | 3 | Verifica jogada | 12 | 6.5
Mecânica | 16 | 13 | - | [6 empty] | Tabuleiro | 10 | 5
Árvore de busca | 10 | 4 | [7 empty] | Peças | 3 | 2
Jogador IA | 4 | 3 | [5 empty] | 2016-10-31 | 4 | Árvore de busca | 10 | 4
Peças | 3 | 2 | [7 empty] | Jogador IA | 4 | 3
Tabuleiro | 10 | 5 | [7 empty] | Verifica status | 5 | 3
Interface | 4 | 1 | [5 empty] | 2016-11-14 | 5 | Interface | 4 | 1
Prototipagem | 8 | 7 | [7 empty] | Prototipagem | 8 | 7
Slides 1 | 2 | 3.5 | [7 empty] | Testes e reparos 1 | 10 | 5
Slides 2 | 10 | 15 | [5 empty] | 2016-11-28 | 6 | Slides 2 | 10 | 15
Slides 3 | 10 | 5 | - | [6 empty] | Apresentacao 2 | 2 | 2.5
Testes e reparos 1 | 10 | 5 | [7 empty] | Testes e reparos 2 | 20 | 32
Testes e reparos 2 | 20 | 32 | [7 empty] | Controller | 5 | 7
Testes e reparos 3 | 10 | 60 | - |  |  |  |  | 2016-12-12 | 7 | Mecânica | 16 | 13
Apresentacao 1 | 2 | 1.7 | [7 empty] | Testes e reparos 3 | 10 | 60
Apresentacao 2 | 2 | 2.5 | [7 empty] | Slides 3 | 10 | 5
Apresentacao 3 | 2 | 2.5 | - | [6 empty] | Apresentacao 3 | 2 | 2.5
Sprint 3
|  |  |  | Dia | Real | Estimado
|  |  |  | 2016-10-17 | 25 | 25
|  |  |  | 2016-10-19 | 25 | 21.4286
|  |  |  | 2016-10-21 | 25 | 17.8571
|  |  |  | 2016-10-23 | 25 | 14.2857
|  |  |  | 2016-10-25 | 25 | 10.7143
|  |  |  | 2016-10-27 | 25 | 7.1429
|  |  |  | 2016-10-29 | 25 | 3.5714
|  |  |  | 2016-10-31 | 13 | 0
Sprint 4
|  |  |  | Dia | Real | Estimado
|  |  |  | 2016-10-31 | 32 | 32
|  |  |  | 2016-11-02 | 32 | 27.4286
|  |  |  | 2016-11-04 | 32 | 22.8571
|  |  |  | 2016-11-06 | 22 | 18.2857
|  |  |  | 2016-11-08 | 22 | 13.7143
|  |  |  | 2016-11-10 | 22 | 9.1429
|  |  |  | 2016-11-12 | 22 | 4.5714
|  |  |  | 2016-11-14 | 18 | 0
Sprint 5
|  |  |  | Dia | Real | Estimado
|  |  |  | 2016-11-14 | 40 | 40
|  |  |  | 2016-11-16 | 35 | 34.2857
|  |  |  | 2016-11-18 | 35 | 28.5714
|  |  |  | 2016-11-20 | 30 | 22.8571
|  |  |  | 2016-11-22 | 27 | 17.1429
|  |  |  | 2016-11-24 | 17 | 11.4286
|  |  |  | 2016-11-26 | 9 | 5.7143
|  |  |  | 2016-11-28 | 9 | 0
Sprint 6
|  |  |  | Dia | Real | Estimado
|  |  |  | 2016-11-28 | 46 | 46
|  |  |  | 2016-11-30 | 26 | 39.4286
|  |  |  | 2016-12-02 | 14 | 32.8571
|  |  |  | 2016-12-04 | 14 | 26.2857
|  |  |  | 2016-12-06 | 14 | 19.7143
|  |  |  | 2016-12-08 | 14 | 13.1429
|  |  |  | 2016-12-10 | 14 | 6.5714
|  |  |  | 2016-12-12 | 14 | 0
|  |  |  | Dia | Real | Estimado
|  |  |  | 2016-12-12 | 52 | 52
|  |  |  | 2016-12-14 | 52 | 39
|  |  |  | 2016-12-16 | 52 | 26
|  |  |  | 2016-12-18 | 26 | 13
|  |  |  | 2016-12-20 | 0 | 0
Formulas:
Dia = [Dia, row above]+2

## Plan2
| Planed Value (PV) | Actual Cost (AC) | Earned Value (EV)
0 | 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
0
0
0
0
Dia | Sprints | Tarefas | Horas | Horas Gastas
2016-09-19 | 1 | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF!
2016-10-03 | 2 | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF!
2016-10-17 | 3 | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF!
2016-10-31 | 4 | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF!
2016-11-14 | 5 | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF!
2016-11-28 | 6 | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF!
2016-12-12 | 7 | Controller | #REF! | #REF!
|  | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF!